## Test Cases
Gym Membership Management System — Software Test Case Matrix
Test Case ID | Test Level | Module / Feature | Test Objective | Precondition | Test Steps | Test Input | Expected Output | Actual Output | Status | Tested By | Date
TC-U01 | Unit | Member Registration | Verify email field rejects invalid email formats | Registration form is open | Enter an improperly formatted email address (e.g., member#gym.com) in the Email field and submit | member#gym.com | System displays 'Invalid email format' and blocks submission | As expected | Pass | Member A | 2026-08-13
TC-U02 | Unit | Member Registration | Verify phone number field accepts only 10-digit numeric input | Registration form is open | Enter a 7-digit phone number and submit | 9812345 | System displays 'Phone number must be 10 digits' | System accepted the 7-digit number and saved it without displaying a validation error | Fail | Member A | 2026-08-13
TC-U03 | Unit | Authentication | Verify password field enforces minimum strength rule | Login/registration form is open | Enter a password shorter than 8 characters | pass1 | System rejects password and shows strength requirement message | As expected | Pass | Member A | 2026-08-13
TC-U04 | Unit | Membership | Verify membership expiry date is calculated correctly for a monthly plan | Plan duration = 1 month, start date known | Select Monthly plan with start date 2026-08-01 | Start: 2026-08-01, Plan: Monthly | System calculates expiry date as 2026-09-01 | As expected | Pass | Member A | 2026-08-14
TC-U05 | Unit | Payment | Verify payment amount field rejects negative or zero values | Payment form is open | Enter -500 as payment amount | -500 | System displays 'Amount must be greater than zero' | As expected | Pass | Member A | 2026-08-14
TC-I01 | Integration | Registration + Payment | Verify successful registration triggers payment module correctly | Member has completed registration form | Submit valid registration data and proceed to payment | Valid member data + Rs. 3000 (Quarterly plan) | Payment module opens with correct plan amount pre-filled | As expected | Pass | Member B | 2026-08-15
TC-I02 | Integration | Attendance + Member DB | Verify check-in updates member's attendance record in the database | Member has an active membership | Receptionist enters member ID at check-in kiosk | Member ID: M1042 | Attendance record is created with correct timestamp and linked member ID | As expected | Pass | Member B | 2026-08-15
TC-I03 | Integration | Class Booking + Trainer Schedule | Verify booking a class updates the trainer's schedule view | Class has available capacity | Member books a Zumba class for 6:00 PM slot | Class ID: C007, Time: 18:00 | Trainer's schedule reflects the new booking and updated headcount | Booking was saved, but the trainer's schedule view still showed the old headcount until the page was manually refreshed | Fail | Member B | 2026-08-16
TC-I04 | Integration | Renewal + Notification | Verify a successful renewal triggers a confirmation notification | Member's membership is near expiry | Member completes renewal payment | Renewal for Member M1042 | System sends confirmation notification/email within the same session | As expected | Pass | Member B | 2026-08-16
TC-I05 | Integration | Admin + Staff Accounts | Verify new staff account creation integrates with role-based access control | Admin is logged in | Admin creates a Receptionist account and assigns role | Username: r.thapa, Role: Receptionist | New account is created with Receptionist-level permissions only | As expected | Pass | Member B | 2026-08-16
TC-S01 | System | End-to-End Registration | Verify complete registration flow from form entry to confirmation | User is on the homepage | Fill registration form, select plan, complete payment, receive confirmation | New member data + Annual plan payment | Member account is created, membership is active, confirmation is displayed | As expected | Pass | Member A | 2026-08-17
TC-S02 | System | End-to-End Renewal | Verify complete renewal flow from login to updated membership status | Member has an existing account nearing expiry | Log in, navigate to renewal, select plan, pay, confirm | Existing member, Monthly renewal | Membership end date is extended and status shows 'Active' | As expected | Pass | Member A | 2026-08-17
TC-S03 | System | Reporting | Verify monthly revenue report reflects all completed payments for the period | Multiple payments recorded within the month | Gym Manager generates revenue report for August 2026 | Report period: Aug 2026 | Report totals match the sum of all recorded payments for August | As expected | Pass | Member B | 2026-08-18
TC-S04 | System | Search & Check-in | Verify receptionist can locate a member and check them in within one workflow | Member exists in the system | Search member by name, open profile, perform check-in | Search term: 'Sujata Gurung' | Correct member profile appears and check-in is recorded successfully | As expected | Pass | Member B | 2026-08-18
TC-S05 | System | Class Capacity | Verify system prevents booking beyond a class's maximum capacity | Class is at full capacity (e.g., 20/20) | Member attempts to book a fully booked class | Class ID: C007 (Full) | System displays 'Class is full' and does not create a booking | Two members booking the same slot simultaneously both succeeded, resulting in 21/20 capacity (limit not enforced under concurrent requests) | Fail | Member B | 2026-08-18
TC-A01 | UAT | Front Desk Operations | Receptionist registers a walk-in member during a simulated busy period | Receptionist role logged in | Perform full walk-in registration using sample walk-in data | Walk-in member: Anish Rai | Registration completes in under 3 minutes with accurate data stored | As expected | Pass | Member A | 2026-08-19
TC-A02 | UAT | Member Self-Service | Member renews their own membership through the member portal | Member account with expiring plan | Member logs in and completes self-service renewal | Member: Priya Shrestha | Renewal completes without staff assistance and status updates immediately | As expected | Pass | Member A | 2026-08-19
TC-A03 | UAT | Management Reporting | Gym Manager reviews the revenue report to support a pricing decision | Report data available for prior month | Manager opens and reviews the monthly revenue report | Report period: July 2026 | Manager confirms the report is clear, accurate, and usable for decisions | As expected | Pass | Member B | 2026-08-20
TC-A04 | UAT | Trainer Workflow | Trainer checks their assigned class schedule for the day before sessions begin | Trainer account with assigned classes | Trainer logs in and views today's schedule | Trainer: Bikash Thapa | Schedule displays all assigned classes with correct times and rosters | As expected | Pass | Member B | 2026-08-20
TC-A05 | UAT | Admin Operations | Admin creates a new receptionist account as part of onboarding | Admin logged in | Admin completes new staff account creation form | New staff: Reception - Kalanki Branch | Account is created, credentials issued, and role restricted appropriately | As expected | Pass | Member B | 2026-08-20

## Summary
Test Level | Number of Test Cases | Pass | Fail
Unit |  | 4 | 1
Integration |  | 4 | 1
System |  | 4 | 1
UAT |  | 5 | 0
Total |  | 17 | 3