## Product Backlog
ID | Actor | User Story | Priority | Story Points | Status
US-01 | Member | As a new member, I want to register for a membership online, so that I can join without visiting the front desk in person. | High | 5 | Done
US-02 | Member | As a member, I want to log in securely, so that I can access my account and membership details. | High | 3 | Done
US-03 | Member | As a member, I want to view and select a membership plan (Monthly/Quarterly/Annual), so that I can pick one matching my needs. | High | 3 | Done
US-04 | Member | As a member, I want to pay for my plan online, so that my registration or renewal is completed immediately. | High | 5 | Done
US-05 | Receptionist | As a receptionist, I want to check members in at the front desk, so that attendance is tracked accurately. | Medium | 3 | In Progress
US-06 | Member | As a member, I want to book a fitness class, so that I can reserve a spot in a session I want to attend. | Medium | 5 | In Progress
US-07 | Trainer | As a trainer, I want to view my assigned class schedule, so that I know which sessions I am teaching and when. | Medium | 2 | To Do
US-08 | Member | As a member, I want to renew my membership before it expires, so that I do not lose access to the gym. | High | 3 | To Do
US-09 | Gym Manager | As a gym manager, I want to generate a monthly revenue report, so that I can track business performance. | Medium | 5 | To Do
US-10 | Admin | As an admin, I want to create staff accounts with role-based access, so that each staff member only has the permissions they need. | Low | 3 | To Do