## Sprint 1 Plan
Task | User Story | Owner | Deadline | Status | Notes
Design registration form fields & validation rules | US-01 | Pralin | Aug 06, 2026 | Done | Define registration data and validation rules.
Design login & authentication flow | US-02 | Shreejan | Aug 07, 2026 | Done | Document secure login and authentication flow.
Define plan options, pricing, and expiry logic | US-03 | Pralin | Aug 08, 2026 | Done | Define Monthly, Quarterly, and Annual plans.
Design payment workflow & data fields | US-04 | Shreejan | Aug 09, 2026 | Done | Document payment information and workflow.
Design front-desk check-in / attendance flow | US-05 | Pralin | Aug 10, 2026 | In Progress | Define check-in and attendance timestamp process.
Document Sprint 1 stand-up notes & prepare retrospective | All Sprint 1 items | Shreejan | Aug 17, 2026 | In Progress | Record sprint progress and prepare reflection.